## week 1
STT | Issue | Hours | number of day | Start time | end time | Personal | note | status
1 | cài đặt JSF và gắn vô eclipse | 4 | 0.5 | 2012-11-04 | 2012-11-04 | Tuấn |  | done | done
2 | cài đặt liferay, gắp liferay vô cho eclipse, | 6 | 3 | 2012-11-04 | 2012-11-06 | Bé |  | done | on going
3 | cài đặt service builder cua liferay --> ket noi csdl | 2 | 1 | 2012-11-07 | 2012-11-07 | Bé |  | on going
4 | gắp và cấu hình hibernate cho eclipse | 4 | 2 | 2012-11-08 | 2012-11-09 | Bé |  | on going
5 | cài dặt websservice axis 2 | 4 | 0.5 | 2012-11-04 | 2012-11-04 | Tuấn |  | done
| specs dưới góc nhìn của ng dùng | 8 | 1 | 2012-11-05 | 2012-11-05 | Tuấn |  | on going
6 | làm use case, liệt kê chức năng | 16 | 2 | 2012-11-06 | 2012-11-07 | Tuấn |  | on going
|  | 8 | 4 | 2012-11-09 | 2012-11-10 | Bé |  | on going
7 | lên giao diện PS | 14 | 2 | 2012-11-08 | 2012-11-09 | Tuấn |  | on going
8 | tạo rule cho code | 4 | 0.5 | 2012-11-10 | 2012-11-10 | Tuấn |  | on going
9 | Tổng tiếng | 70
10 | Tuấn | 56
11 | Bé | 14
12 | Chuẩn | 70
13
14 | Android
15
16
17
18
19
20
21
22
23

## week 2
STT | Issue | Hours | number of day | Start time | end time | Personal | note | status
| cài đặt service builder cua liferay --> ket noi csdl | 2 | 1 | 2012-11-12 | 2012-11-12 | Bé |  | on going
| gắp và cấu hình hibernate cho eclipse | 2 | 1 | 2012-11-13 | 2012-11-13 | Bé |  | on going
Viet đặc tả Use case
| Quản lý kho món ăn | 2 | 1 |  |  | Bé |  |  | Bé
| Chọn món ăn trong ngày | 2 | 1 |  |  | Bé |  |  | Tuấn
| Cập nhật trạng thái món ăn | 2 | 1 |  |  | Bé
| Xem menu | 2 | 1 |  |  | Bé
| Gọi món ăn | 2 | 1 |  |  | Bé
| Thanh toán | 2 | 0.25 |  |  | Tuấn
| Quản lý món ăn đã gọi | 2 | 0.25 |  |  | Tuấn
| Góp ý | 2 | 0.25 |  |  | Tuấn
| Quản lý hóa đơn | 2 | 0.25 |  |  | Tuấn
| Quan lý khuyễn mãi | 2 | 0.25 |  |  | Tuấn
| Cập nhận các món đã gọi | 2 | 0.25 |  |  | Tuấn
| Kiểm soát trạng thái bàn | 2 | 0.25 |  |  | Tuấn
| Quảng cáo | 2 | 0.25 |  |  | Tuấn
| tạo rule cho code | 4 | 0.5 | 2012-11-10 | 2012-11-10 | Tuấn |  | on going
| Tổng tiếng | 34
| Tuấn | 56
| Bé | 14
| Chuẩn | 70